# Team E Implementation Task Backlog

CareConnect — Ordered by importance and dependencies

Consolidates implementation tasks from all Team E research documents. Tasks earlier in the document unblock everything below them.

Legend — Owner: A = Team A (video/summaries/Bedrock), E = Team E (Ask AI/safety/retrieval), P = Platform/infra, SUM = Summaries workstream, FE = Frontend.

Yellow highlights mark critical-path or safety-blocking items.

# 1. Executive Overview

Eight research documents identified gaps between Team E SRS/TDD requirements and the current codebase (post origin/main baseline). This backlog organizes ~50 tasks into nine tiers. Tier 0–2 are foundation work; Tier 3–5 build the Ask AI data path; Tier 6–7 add safety and voice; Tier 8 covers resilience and test automation.

Do not ship patient-facing Ask AI without RetrievalScopeService (2.1) and Safety/HITL (6.1–6.3).

Lock unified summary_json (1.1) and retrieval_index_chunk (1.5) before parallel indexing work.

Medication timeline (FR-AI-11) is derived indexing + query planning — not a separate retrieval system.

Voice query reuses the text Ask AI gateway after Tier 5 and Tier 6 are in place.

Team A coupling (summaries, sentiment, IAM, transcripts) is the main external dependency for Team E.

## 1.1 Source research documents

docs/Call_Transcript_Retrieval_Review.docx

docs/Hybrid_Retrieval_Scope_PostgreSQL_FullText_pgvector.docx

docs/Ask_AI_Upstream_Pipeline_Call_Visit_Summaries.docx

docs/RBAC_Scoped_Retrieval_Source_Types.docx

docs/Voice_Query_Path_and_STT_Framework_Dependencies.docx

docs/Medication_Timeline_Retrieval_FR-AI-11.docx

docs/HITL_Tier1_Tier2_Escalation_and_Hold_Release_Workflow.docx

docs/LLM_Provider_Abstraction_Bedrock_TeamA_BAA_Fallback.docx

# 2. Tier 0 — Platform Prerequisites

Blocks production AI everywhere. Complete before scaling Ask AI or summary features.

| ID | Task | Owner | Depends on | Source research doc(s) |
| --- | --- | --- | --- | --- |
| 0.1 | Extend ECS IAM for Claude inference-profile ARNs (not only Nova Lite/Pro) | P | — | LLM Provider Abstraction |
| 0.2 | Unify LLM config: single policy; prod guardrail blocking DeepSeek/OpenRouter for PHI | E/P | — | LLM Provider Abstraction |
| 0.3 | Introduce LlmRouter / extend AIServiceFactory: Bedrock primary → in-account failover → dev mock | E (+A) | 0.1, 0.2 | LLM Provider Abstraction |
| 0.4 | Refactor BedrockSentimentService to use shared router (not direct BedrockRuntimeClient) | A | 0.3 | LLM Provider Abstraction; Ask AI Upstream |
| 0.5 | Persist provider + model_version on call_summaries and chat audit rows | A/E | 0.3 | LLM Provider Abstraction; Ask AI Upstream |
| 0.6 | Fix AIChatService bean wiring — conditional @Primary; Bedrock vs mock never collide | E | 0.2 | LLM Provider Abstraction |

# 3. Tier 1 — Lock Shared Contracts

Blocks indexing, medication timeline, and Ask AI retrieval. Schema lock is TDD R4 mitigation.

| ID | Task | Owner | Depends on | Source research doc(s) |
| --- | --- | --- | --- | --- |
| 1.1 | Lock unified summary_json schema (careInstructions, conditions, SOAP, citations, episodeType) | A/SUM | — | Ask AI Upstream; Medication Timeline |
| 1.2 | Upgrade Bedrock summary prompt/parser to emit full contract (not reduced subset) | A | 1.1 | Medication Timeline; Ask AI Upstream |
| 1.3 | Schema validation on summary write — reject meds missing status/effectiveDate | A | 1.1 | Medication Timeline |
| 1.4 | Create visit_summaries table + VisitSummaryService mirroring call_summaries | P/SUM | 1.1 | Ask AI Upstream |
| 1.5 | Define and migrate retrieval_index_chunk (pgvector + tsvector, patient_id, record_type) | P/E | — | Hybrid Retrieval; RBAC; Medication Timeline |
| 1.6 | Enable pgvector extension + embedding dimension (1536) in Flyway | P | 1.5 | Hybrid Retrieval |

# 4. Tier 2 — RBAC & Retrieval Scope

Must precede any retrieval or Ask AI that returns patient data.

| ID | Task | Owner | Depends on | Source research doc(s) |
| --- | --- | --- | --- | --- |
| 2.1 | Implement RetrievalScopeService — patient/caregiver/family + consent (REQ-SC-7/8) | E | — | RBAC Scoped Retrieval |
| 2.2 | Grant USE_AI_FEATURES to PATIENT; fix symptom permission gaps | E | — | Voice Query; RBAC Scoped Retrieval |
| 2.3 | Index all chunks with patient_id; enforce patient filter on every query | E | 1.5, 2.1 | RBAC Scoped Retrieval |
| 2.4 | Add caregiver_visibility on summary rows; exclude restricted chunks for caregivers | A/E | 1.4, 2.1 | RBAC Scoped Retrieval |
| 2.5 | Scope USPS mail by mailbox owner → patient; allow patient retrieval of own mail | E | 2.1 | RBAC Scoped Retrieval |
| 2.6 | 403 + audit on cross-patient / unauthorized source access (no AI output) | E | 2.1 | RBAC Scoped Retrieval; HITL |

# 5. Tier 3 — Transcript & Upstream Pipeline

Feeds the retrieval index with complete transcript and summary data.

| ID | Task | Owner | Depends on | Source research doc(s) |
| --- | --- | --- | --- | --- |
| 3.1 | Composite DB index on call_transcript_segments (call_id, start_ms, occurred_at) | P | — | Call Transcript Retrieval Review |
| 3.2 | Reliable transcript ingest — client segments + post-call Transcribe; fix S3 null in dev | A | — | Call Transcript Retrieval Review |
| 3.3 | Summary regen hook when post-call transcription completes | A | 3.2 | Call Transcript Retrieval; Voice Query |
| 3.4 | Emit SUMMARY_CREATED / TRANSCRIPT_INDEXED events (or polling job) for indexer | A/E | 1.2, 3.2 | Hybrid Retrieval; Ask AI Upstream |
| 3.5 | Single chunker for call + visit summaries (same inner JSON, different envelope) | E | 1.1, 1.4 | Ask AI Upstream; Hybrid Retrieval |

# 6. Tier 4 — Indexing Pipeline

Blocks grounded Ask AI answers with citations.

| ID | Task | Owner | Depends on | Source research doc(s) |
| --- | --- | --- | --- | --- |
| 4.1 | RetrievalIndexService — ingest per record type (TRANSCRIPT, SUMMARY, DOCUMENT, NOTE, USPS) | E | 1.5, 2.3, 3.4 | Hybrid Retrieval; RBAC |
| 4.2 | FTS: maintain search_vector via trigger or application on insert/update | E | 4.1 | Hybrid Retrieval |
| 4.3 | Embeddings: batch embed chunk_text via Bedrock Titan or approved embed model | E | 0.3, 4.1 | Hybrid Retrieval |
| 4.4 | Embedding backfill worker + optional SchemaPatchRunner NULL-embedding partial index (no Flyway at deploy) | E | 4.1–4.3, 3.2 | Hybrid Retrieval; Transcript Review |
| 4.5 | Derived index MEDICATION_TIMELINE_EVENT from careInstructions type=medication | E | 1.2, 4.1 | Medication Timeline FR-AI-11 |
| 4.6 | Medication name normalization at index time (RxNorm or alias list) | E | 4.5 | Medication Timeline FR-AI-11 |

Task 4.4 deliverables: ChunkEmbeddingBackfillWorker scheduled poll, findMissingEmbeddingsForBackfill / countMissingEmbeddingsForBackfill repository queries, careconnect.embedding.backfill.* properties, and reuse of ChunkEmbeddingService.embedAndPersist. Optional DBA follow-up (not blocking MVP): SchemaPatchRunner partial index idx_retrieval_chunk_embedding_null_backfill (reference SQL V2607161317) when NULL-embedding backlog is large. No Flyway at ECS deploy.

Core Team E deliverable — records-grounded Ask AI.

| ID | Task | Owner | Depends on | Source research doc(s) |
| --- | --- | --- | --- | --- |
| 5.1 | HybridRetrievalService — scoped prefilter → FTS + vector → RRF → top-k citations | E | 2.1, 4.1–4.3 | Hybrid Retrieval |
| 5.2 | Medication intent planner — prefilter MEDICATION_TIMELINE_EVENT (FR-AI-11) | E | 4.5, 5.1 | Medication Timeline FR-AI-11 |
| 5.3 | POST /api/ai/ask — JWT, scope, retrieval, prompt, min-necessary context (FR-AI-9) | E | 5.1, 2.1 | Hybrid Retrieval; Ask AI Upstream |
| 5.4 | Re-wire MedicalContextService into Bedrock path (replace raw-message-only chat) | E | 5.3 | Ask AI Upstream; LLM Abstraction |
| 5.5 | Citation builder — type, id, excerpt, deep link (FR-AI-2) | E | 5.1 | Hybrid Retrieval; RBAC |
| 5.6 | No-records path — explicit message; no general medical answer (FR-AI-2) | E | 5.1 | Hybrid Retrieval |
| 5.7 | Flutter Ask AI screen — citations, disclaimer, confirm-with-provider prompt | E/FE | 5.3 | Ask AI Upstream; HITL |
| 5.8 | Deprecate PatientContextRetrievalService stub; single hybrid path only | E | 5.1 | Ask AI Upstream |

# 8. Tier 6 — Safety, Consent & HITL

Must wrap delivery before patient-facing rollout. Tier 2 hold is an SRS hard requirement.

| ID | Task | Owner | Depends on | Source research doc(s) |
| --- | --- | --- | --- | --- |
| 6.1 | SafetyValidationService + TierClassifier (SRS Table 8 rules) | E | — | HITL Tier 1–2 Escalation |
| 6.2 | held_item schema + HITL queue API (PENDING → APPROVED/REJECTED) | E | 6.1 | HITL Tier 1–2 Escalation |
| 6.3 | Integrate SCC-3 steps 11–16 into Ask AI gateway — tier assign → hold or deliver | E | 5.3, 6.1 | HITL; Hybrid Retrieval |
| 6.4 | Human Reviewer role + release/reject endpoints | E | 6.2 | HITL Tier 1–2 Escalation |
| 6.5 | Client held-state UX — review message + poll/WebSocket until release | E/FE | 6.2, 6.3 | HITL Tier 1–2 Escalation |
| 6.6 | Confirmation workflow — approve once / session / decline (REQ-SC-5/6) | E | 5.3 | HITL Tier 1–2 Escalation |
| 6.7 | Extend HITL to summary items — med-change confirm (FR-SUM-4) | E/A | 6.1, 1.2 | HITL; Medication Timeline |
| 6.8 | Immutable audit ledger — query, tier, hold, release, citations (REQ-SC-9) | E | 6.3 | HITL; RBAC |

# 9. Tier 7 — Voice Query & STT

After text Ask AI and safety gateway are working.

| ID | Task | Owner | Depends on | Source research doc(s) |
| --- | --- | --- | --- | --- |
| 7.1 | Mic on Ask AI → speech_to_text → existing text pipeline | E/FE | 5.3, 2.2 | Voice Query Path |
| 7.2 | Document STT ownership — Chime live vs post-call Transcribe vs client STT | A/E | 3.2, 3.3 | Voice Query; Transcript Review |
| 7.3 | Voice path through same SCC-3 — RBAC → retrieval → safety → HITL | E | 5.3, 6.3, 7.1 | Voice Query; HITL |

# 10. Tier 8 — Resilience, Ops & Test Automation

| ID | Task | Owner | Depends on | Source research doc(s) |
| --- | --- | --- | --- | --- |
| 8.1 | Bedrock throttling: exponential backoff + retry queue (SRS UC-SUM 2a) | A/E | 0.3 | LLM Provider Abstraction |
| 8.2 | Dev mock summary when Bedrock not provisioned (SRS UC-SUM 2b) | A | 0.3 | LLM Provider Abstraction |
| 8.3 | Automate TC-E-SC-001, TC-AI-06, TC-SCC-03, FR-AI-11, hybrid retrieval tests | E | Tier 5–6 | All test-plan refs |
| 8.4 | Update PROGRAMMERS_GUIDE — Bedrock primary, abstraction, retrieval, HITL | E/Docs | Tier 0–6 | LLM Provider Abstraction |
| 8.5 | Spanish safety copy review-verified (SRS NFR) | E | 6.3 | HITL Tier 1–2 Escalation |
| 8.6 | Monitoring: retrieval latency, index lag, HITL queue depth, provider failover | P/E | Tier 4–6 | Hybrid Retrieval; HITL |

# 11. Critical Path — Minimum Viable Ask AI with Safety

0.1–0.3  LLM router + IAM
    ↓
1.1–1.5  Unified schema + retrieval_index_chunk
    ↓
2.1        RetrievalScopeService
    ↓                    ↓
3.2–3.4  Transcript/events     4.1–4.3  Indexing pipeline
    ↓                    ↓
    └──────────┬─────────┘
               ↓
5.1–5.6  Hybrid retrieval + POST /api/ai/ask
               ↓
6.1–6.3  SafetyValidation + TierClassifier + HITL hold
               ↓
7.x      Voice query (optional extension)
5.2      Medication timeline (parallel after 4.5 + 5.1)

# 12. Parallel Workstreams (after Tier 1 schema lock)

| Stream | Can start after | Task IDs |
| --- | --- | --- |
| Team A — Summaries | 1.1 | 1.2, 1.3, 1.4, 3.3, 0.4 |
| Platform — Index DB | — | 1.5, 1.6, 3.1 |
| Team E — RBAC | — | 2.1–2.6 (parallel with 1.5) |
| Team E — Indexer | 1.5, 2.3, 3.4 | 4.1–4.6 |
| Team E — Ask AI | 4.1, 2.1 | 5.1–5.8 |
| Team E — Safety | 5.3 (design earlier) | 6.1–6.8 |
| Voice | 5.3, 6.3 | 7.1–7.3 |

# 13. Key Dependency Rules

| If you need… | You must complete first… |
| --- | --- |
| Grounded Ask AI answers | 1.5, 2.1, 4.1–4.3, 5.1 |
| Medication timeline (FR-AI-11) | 1.2, 4.5, 5.1, 5.2 |
| Tier 2 hold before patient sees answer | 5.3, 6.1, 6.2, 6.3 |
| Voice Ask AI | 5.3, 6.3, 7.1 |
| Claude in ECS production | 0.1 (IAM) |
| Visit summary retrieval | 1.4, 3.5, 4.1 |
| Caregiver-scoped summaries | 2.4, 2.1 |
| BAA-compliant prod inference | 0.2, 0.3 (block non-BAA providers) |

# 14. Suggested Milestone Mapping

| Milestone | Tiers / tasks | Outcome |
| --- | --- | --- |
| M2 completion / hardening | 0.1–0.6, 1.1–1.3 | Bedrock reliable; summary contract locked |
| M3 — Retrieval foundation | 1.5–1.6, 2.1–2.6, 3.1–3.5 | Index schema + scope + upstream events |
| M3 — Ask AI alpha | 4.1–4.4, 5.1–5.6 | Internal /api/ai/ask with citations |
| M3 — Safety gate | 6.1–6.5, 6.8 | Tier 2 hold + reviewer workflow |
| M3 — Feature complete | 4.5–4.6, 5.2, 5.7, 6.6–6.7, 7.1–7.3 | Med timeline, voice, summary confirm |
| M3 — Production ready | 8.1–8.6 | Failover, tests, monitoring, docs |

# 15. Complete Task Index (all IDs)

Quick reference — 47 tasks across nine tiers.

Tier 0: 0.1, 0.2, 0.3, 0.4, 0.5, 0.6
Tier 1: 1.1, 1.2, 1.3, 1.4, 1.5, 1.6
Tier 2: 2.1, 2.2, 2.3, 2.4, 2.5, 2.6
Tier 3: 3.1, 3.2, 3.3, 3.4, 3.5
Tier 4: 4.1, 4.2, 4.3, 4.4, 4.5, 4.6
Tier 5: 5.1, 5.2, 5.3, 5.4, 5.5, 5.6, 5.7, 5.8
Tier 6: 6.1, 6.2, 6.3, 6.4, 6.5, 6.6, 6.7, 6.8
Tier 7: 7.1, 7.2, 7.3
Tier 8: 8.1, 8.2, 8.3, 8.4, 8.5, 8.6

# 16. Related Documents

C:\Users\ravic\Downloads\CareConnect_SRS_Revision 2.0_TEAM E.docx

C:\Users\ravic\Downloads\CareConnect_Milestone_2_TDD_TEAM E.docx

C:\Users\ravic\Downloads\CareConnect_Milestone_2_Software_Test_Plan (2).docx

docs/Call_Transcript_Retrieval_Review.docx

docs/Hybrid_Retrieval_Scope_PostgreSQL_FullText_pgvector.docx

docs/Ask_AI_Upstream_Pipeline_Call_Visit_Summaries.docx

docs/RBAC_Scoped_Retrieval_Source_Types.docx

docs/Voice_Query_Path_and_STT_Framework_Dependencies.docx

docs/Medication_Timeline_Retrieval_FR-AI-11.docx

docs/HITL_Tier1_Tier2_Escalation_and_Hold_Release_Workflow.docx

docs/LLM_Provider_Abstraction_Bedrock_TeamA_BAA_Fallback.docx

# 17. Conclusion

This backlog is the single ordered implementation plan derived from Team E research. Schedule Tier 0 and Tier 1 in the same sprint as Team A summary and IAM work. Do not expose Ask AI to care recipients until Tier 2 scope enforcement and Tier 6 safety/HITL are integrated into the same gateway path as POST /api/ai/ask.